## Instructions
Instructions to Raters:
Make sure that you read the PM and STAFF guidelines that will assist you in
determining what a "1" thru a "5" mean for each item.
ONLY ENTER INFORMATION ON EACH SHEET THAT IS SHADED IN BLUE.
1. Fill out all portions of the "cover" sheet that are shaded in blue. If not
applicable, type "n/a".
2. Enter "1" thru "5" for each question on the PM Rating sheet in the blue boxes.
Use the guidelines for your answers that are on the PM Guidelines sheet.
Enter an "X" in the N/A column for each item that is not applicable for rating the
project management of the firm. You must explain all N/A's, 1's and 5's.
The rating will be automatically generated.
Do not WRITE or TYPE anything else on this sheet.
3. Enter "1" thru "5" for each item that is applicable for your field staff.
Use the guidelines for your answers that are on the Staff Guidelines sheet.
If you have any categories that are "n/a", put an X in the n/a column.
You must explain all N/A's, 1's and 5's.
Note: Environmental and Traffic questions pertain to ALL staff on your project.
There should definitely NOT be an "X" in the "n/a" column for safety, and
there should SELDOMLY be an "X" in the "n/a" column for environmental.
Note: if you do not have either a Lead Insp or a Consultant RE (or scheduler), every
item will be marked with an "X" in the n/a column for that section of the rating sheet.
The rating will be automatically generated as an average of all of your rated items.
4. On the CES sheet, the rating period and cycle have been entered for you.
Enter the Rating type (final or 6 month) in the box shown. Enter remarks.
If you need to attach separate sheets for remarks, print "see attached" in the
remarks boxes. (Fill in all the blue boxes on this sheet.)
5. Sign the blue boxes on the CES sheet after printing out.
6. Remarks are MANDATORY, even if you are rating the consultant as a "5".
You may put them on sheet CES or on a separate sheet of paper, if needed.
A brief remark is needed for n/a's.
7. Send 4 signed copies of all four sheets to the Regional Invoice Coordinator.
Assemble them in the following order: CES, Cover, pm rating, staff rating.
Do not send in copies of the rating guidelines. You may keep them for your use
for the next rating cycle.
Note: there is NO NEED to print these out in color; black print is fine.
For rating cycle 18, email your rating to Lynn Bartleson. She will review it and will answer some of the PM
questions for you, and then email it back to you. Then print out one copy, sign it, have the reviewer sign it, and send one copy
to Sean Sheehy, Office of the Director, CS&M, 2nd floor E&O. He will compile them and make copies.

## CES
| Project Description | #REF! | [7 empty] | Consultants | Rating Type | Contract Type | [5 empty] | division/unit | cycle
[11 empty] | 6 Month |  |  |  |  | 5
| Contract Agreement Type | Consultant Material Inspection | [7 empty] | *Other (see comments) | NR | *Other (see comments) |  | January - June | Construction Inspection | 4 | Agreement | Other | 11
[10 empty] | Abbington Associates | Final | Asbestos Remediation Term Agreement |  | February - July | DESIGN-Construction Phase | 3 | Modification | Bicycle/Pedestrian | 12
[10 empty] | Amy S. Greene Environmental | Averaged | Bicycle/Pedestrian Planning |  | July - December | DESIGN-Design Phase | 2 |  | Capital Program Management | 13
| Consultant | XYZ Consultants, Inc. | [7 empty] | Archelolgical & Historical Consultants |  | Bridge Painting Contract |  | August - January | DESIGN-Overall Quality | 1 |  | Civil Engineering | 14
|  | 2005 BCE 868 |  |  | UPC# | #REF! |  | Agreement/ Modification | Agreement | Arora & Associates |  | Concept Development Study |  |  | Maintenance | 0 |  | Construction Services | 15
[10 empty] | ATC Environmental Associates |  | CPM |  |  | Planning |  |  | Construction, Central | 16
|  | Joe Q. Project |  | Rating Period | Oct 1 - Sep 30 | Year | 2013-2014 |  | 24
[11 empty] | Bergman Associates |  | Local Roadway Inventory, Central
[10 empty] | Chas. H. Sells |  | Local Roadway Inventory, North | [5 empty] | Project Planning & Development, North
| Division/Unit: | Construction Services and Materials/ Bureau of Materials | [7 empty] | Cherry Weber & Associates |  | Local Roadway Inventory, South | [5 empty] | Project Planning & Development, South
[6 empty] | (no signature required) |  |  |  | Chilton Engineering |  | Local Technical Assistance | [5 empty] | Statewide Planning
|  |  | Eileen Sheehy | [6 empty] | Chilton Engineering |  | Local Technical Assistance | [5 empty] | Statewide Planning
|  |  | Type Name |  |  | Signature & Date |  |  |  | Churchill, PC |  | Maintenance Management System | [5 empty] | Structural Engineering
|  |  | Fred Lovett | [6 empty] | Clough Harbour & Associates |  | Maintenance Resurfacing Contract | [5 empty] | Structural Evaluation
|  |  | Type Name |  |  | Signature & Date |  |  |  | Collins Engineers |  | Maintenance Roadway Repair Contract | [5 empty] | Traffic Access
[7 empty] | (enter "Interim" or "Final" below) |  |  | Consoer Townsend Envirodyne Engineers |  | Pavement Management Systems, Statewide | [5 empty] | Transportation Data Development
Discipline: | Construction Inspection | [5 empty] | Rating Type: | Interim |  | Consolidated Resource Management |  | Statewide Needs Assessment
|  |  | 0% | [6 empty] | Consulting Engineer Services |  | Straight Line Diagram
[10 empty] | CV Associates |  | Task Order Agreement, Central
| C a t e g o r y R a t i n g |  |  |  | Weighted Category |  |  |  | 0 | Delta Engineers |  | Task Order Agreement, North
| Schedule | [8 empty] | Dewberry - Goodkind |  | Task Order Agreement, South
Schedule Comments: | [9 empty] | DMJM Harris |  | Task Order Agreement, Statewide
(enter NOTHING here) | [9 empty] | Dresdner Robin Environmental Management |  | Term Agreement, Central
|  |  |  | 0% |  | 0% | 0% |  | 0 | Earth Tech/TAMS |  | Term Agreement, North
| Quality | #REF! |  |  |  |  | 90% |  |  | Edwards & Kelcey |  | Term Agreement, South
Quality Comments: |  |  | 0% | [6 empty] | EL Taller Colaborativo |  | Traffic Monitoring System
[10 empty] | Fay Spofford & Thorndike |  | Transportation Needs Assessment
[6 empty] | 0% | 0% |  | 0 | French & Parrello Associates
| Project Management | #REF! |  |  |  |  | 10% |  |  | Gannett Fleming
Project Management Comments: | [9 empty] | Garg Consulting Services
Garmen Associates
GEOD Corporation
[7 empty] | Total Weighted Category Rating: |  | #REF! | Gibson Associates
Extra Comments: | [9 empty] | Greenman - Pedersen
HAKS Engineers, P.C.
Hardesty & Hanover
Prepared by Bureau of Professional Services | [9 empty] | Harold Pellow & Associates
Hatch Mott MacDonald
HNTB Corporation
Hunter Research
Iffand Kavanaugh Waterbury
Infra Tech Associates
Integrated Engineering
ITX Stanley
Jacobs Civil
Jenny Engineering
John Milner
Kise Straw & Kolodner
KS Engineers
Kupper Associates
L. Robert Kimball & Associates
LDA Consulting
Lichtenstein Consulting Engineers
Lord Worrell & Richtert
Louis Berger Group
LS Engineering Associates Inc.
Maguire Group
Maitra Associates
McCormick Taylor & Associates
McFarland - Johnson
Medina Consultants
Michael Baker Jr.
Modjeski & Masters
Orth - Rogers & Associates
Parsons Brinckerhoff - QD
Parsons Engineering Science
Parsons Transportation
Pennoni Associates
Pickering Corts & Summerson
Polytran Engineering
QBS International
RBA Group
Remington & Vernick Engineers
Schoor DePalma
Site - Blauvelt Engineers
So - Deep
Stantec Consulting
Stone & Webster Engineering
STV, Inc.
T & M Associates
Taylor Wiseman & Taylor
TRC Engineers
Urban Engineers
Urbitran Associates
URS Consultants
Vollmer Associates
W.J. Castle & Associates
Washington Infrastructure
[10 empty] | Weidlinger Associates | [5 empty] | 1
[10 empty] | Weston Engineers | [5 empty] | 0.5
[10 empty] | Wilbur Smith & Associates | [5 empty] | 0
CYCLE
Consultant Agreement #
Consultant Project Manager
Rater's Supervisor
Department's Rater
Rater's Manager

## Cover
CONSULTANT EVALUATION
PROJECT INFORMATION FORM
DIVISION OF PROCUREMENT / BUREAU OF PROFESSIONAL SERVICES
Date: | 2007-04-10
Consultant Firm: | XYZ Consultants, Inc.
Consultant Project Manager: | Joe Q. Project
Vendor ID#: | 21-12343425
(see your invoices)
Agreement #: | 2005 BCE 868
Agreement Date: | 2004-10-29
Agreement Contract Amount: | 1234567.23
Rater's name: | Fred Lovett
Rater's Supervisor's name: | Eileen Sheehy
Design
Planning
Construction Inspection
Materials Inspection
Structural Evaluation and Bridge Maintenance
Maintenance
DEPARTMENT RATING UNIT:
Construction Services and Materials
Distribution: | Note: Send ALL copies to the Regional Consultant
Bureau of Professional Services | Coordinator, and the Region will distribute
Manager | copies as necessary. Make a
Bureau of Construction Management | copy to keep for your own files, if
Consultant Project Manager | you so desire.

## Rating Form
DC-180 October 2009
NEW JERSEY DEPARTMENT OF TRANSPORTATION
CONSULTANT MATERIAL INSPECTION
PERFORMANCE EVALUATION
| Consultant: |  | XYZ Consultants, Inc.
Agreement:
| Rating Period: |  | Oct 1 - Sep 30
| Rater: |  | Fred Lovett
| Reviewer: |  | Eileen Sheehy
[5 empty] | Enter | Enter "X"
| PROJECT MANAGEMENT |  |  | weight | 1 - 5 | if N/A
|  | 1 | Project Manager is available and responsive | 3 | 5 |  | 15 | 15
|  | 2 | Provided qualified staff | 3 | 5 |  | 15 | 15
|  | 3 | Provided staff in a timely manner | 3 | 5 |  | 15 | 15
|  | 4 | Submitted cost proposal, agreement; supporting documents; modifications and task orders in a timely manner | 3 | 5 |  | 15 | 15
|  | 5 | Performed Quality Assurance oversight for assignments | 2 | 5 |  | 10 | 10
|  | 6 | Monitors agreement budget and communicates need for modifications | 1 | 5 |  | 5 | 5
|  | 7 | Invoices are accurate, and submitted in a timely manner. | 2 | 5 |  | 10 | 10
|  | 8 | Met the project's established DBE/ESBE or SBE goals | 1 | 5 |  | 5 | 5
|  | 9 | Provided testing equipment that meets specifications and in calibration | 2 | 5 |  | 10 | 10
|  |  | Overall Project Management Rating |  | 5
[7 empty] | 100 | 100
QUALITY
|  | 1 | Staff demonstrates technical knowledge of materials inspection | 4 | 5 |  | 20 | 20
|  | 2 | Staff is familiar with assignment compliance requirements (standard specification/special provision/ working drawing requirements) | 1 | 5 |  | 5 | 5
|  | 3 | Staff follows NJDOT materials procedures | 1 | 5 |  | 5 | 5
|  | 4 | Reports submitted are detailed and correctly completed | 1 | 5 |  | 5 | 5
|  | 5 | Staff submits reports in a timely manner | 1 | 5 |  | 5 | 5
|  | 6 | Staff communicates effectively with fabricator, supplier, contractor and NJDOT personnel | 2 | 5 |  | 10 | 10
|  | 7 | Supervisory staff exercises oversight/ organizes inspection team to ensure all activities are monitored | 3 | 5 |  | 15 | 15
|  |  | Overall Quality Rating |  | 5
[7 empty] | 65 | 65

## Rating Guidelines
Project Management
RATING
| 1 | 2 | 3 | 4 | 5
Q1 | Frequent difficulty in contacting consultant project manager (or alternate); required multiple attempts via phone calls and e-mails, on multiple occasions did not respond within 2 days. | Some difficulty contacting consultant project manager (or alternate); On more than two occasions required multiple attempts to contact via phone or e-mail; on more than one occasion did not respond within 2 days. | No significant difficulty contacting consultant project manager (or alternate); usually responded to phone calls and e-mails within 24 hours. | Consultant project manager (or alternate) was easily contacted, often responded to phone calls and e-mails within a few hours. | Consultant project manager (or alternate) was easily contacted, responded to phone calls and e-mails, usually less than one hour.
Q2 | When requested for staff, consultant : | When requested for staff, consultant provided staff with the following: | When requested for staff, consultant provided staff with the following: | When requested for staff, consultant provided staff with the following: | When requested for staff, consultant was always able to provide staff with the following:
| Regularly provided staff that only met the Mandatory Requirements | a) met the Mandatory Requirements (Sect. 1B of the Technical Proposal) | a) met the Mandatory Requirements (Sect. 1B of the Technical Proposal) | a) met the Mandatory Requirements (Sect. 1B of the Technical Proposal) | a) met the Mandatory Requirements (Sect. 1B of the Technical Proposal)
| Regularly proposed staff that failed to meet the requested certification and experience qualifications requested for the assignment 1 | b)on multiple occasions, staff did not have the certification and experience profiles requested for assignments. 1 | b) not more than one individual per task did not have the certification qualifications requested for the assignment.1 | b) not more than one individual per task did not have the certification qualifications requested for the assignment.1 | b) had the certification qualifications requested for the assignment1
| 1 -[does not include certification or experience requirements not outlined in the Technical Proposal] | 1 -[does not include certification or experience requirements not outlined in the Technical Proposal] | c) not more than one individual per task did not have the experience qualifications requested for the assignment1 | c) not more than one individual per task did not have the experience qualifications requested for the assignment1 | c) had experience qualifications that met and usually exceeded that requested for the assignment1
|  |  | 1 -[does not include certification or experience requirements not outlined in the Technical Proposal] | 1 -[does not include certification or experience requirements not outlined in the Technical Proposal] | 1 -[does not include certification or experience requirements not outlined in the Technical Proposal]
| Or on at least one occasion was unable to provide sufficient acceptable staff to meet a single assignment..2 | Or was unable to provide sufficient staff to meet multiple assignments on at least one request. 2 | And was able to provide sufficient acceptable staff to meet multiple assignements2 | And was able to provide sufficient acceptable staff to meet multiple assignments.2 | And was able to provide sufficient acceptable staff to meet multiple assignments.2
| 2 - [Up to the staff level submitted in the Technical Proposal] | 2 - [Up to 2X the staff level submitted in the Technical Proposal] | 2 - [Up to 2X the staff level submitted in the Technical Proposal] | 2 - [Up to 2X the staff level submitted in the Technical Proposal] | 2 - [Up to 3X the staff level submitted in the Technical Proposal]
Q3 | On multiple occasions, consultant was unable to provide acceptable staff within requested time frame (not less than 10 days) | On at least one occasion, consultant was unable to provide acceptable staff within requested time frame (not less than 10 days) | Consultant was always able to provide acceptable staff within 10 business days. 1 | Consultant was usually able to provide acceptable staff within 5 business days, with no incidence of providing staff in more than 10 business days.1 | Consultant was always able to provide acceptable staff within 5 business days and usually was able to provide staff less than 3 business days.1
|  |  | 1- [ Except when NJDOT gave longer advance notice.] | 1- [ Except when NJDOT gave longer advance notice.] | 1- [ Except when NJDOT gave longer advance notice.]
Q4 | Slow to submit agreement documents and task orders. Often required reminders to submit documents. | Slow to submit agreement documents and task orders. Required reminders to submit documents. | Usually submits agreement documents within 10 business days and task orders within 3 business days. | Provides submission of agreement documents within 10 business days and task orders within 3 business days. | Consistently provides expedient submission of agreement documents (within 5 business days) and task orders (within 2 business days).
| On multiple occasions, errors by consultants required resubmission resulting in delays, OR at least one error delayed processing by more than 20 days. | On multiple occasions, errors by consultants required resubmission resulting in delays, OR at least one error delayed processing by more than 5 days. | AND documents are usually correct and complete, and any errors do not delay processing by more than 5 days. | AND documents are consistently correct and complete, and do not delay processing. | AND documents are consistently correct and complete, and do not delay processing.
Q5 | Firm has no quality assurance program for staff performance of function. | Firm has quality assurance program that loosely monitors staff performance. | Documented that the firm had a quality assurance program to ensure staff performed functions. | Documented that the firm had a quality assurance program to ensure staff performed functions. | Documented that the firm had a quality assurance program to ensure staff performed functions with a high degree of quality.
|  | OR demonstrated that firm does not adhere to quality assurance program | AND demonstrated that firm monitored staff procedures. | AND demonstrated that firm monitored staff procedures. | AND demonstrated that firm monitored staff procedures to ensure service quality.
Q6 | Exceed budget limits without prior notification to NJDOT. | Informs NJDOT of needs for modifications with less than one month in advance. | Discusses expenses/budget projections with NJDOT, informs the NJDOT of needs for modifications at least one month in advance. | Discusses expenses/budget projections with NJDOT, informs the NJDOT of needs for modifications at least one month in advance. | Discusses expenses/budget projections with NJDOT, informs the NJDOT of needs for modifications at least one month in advance.
|  | [Rating will be moderated if notification could not reasonably have been anticipated (extenuating circumstances). |  | AND identifies tasks that can be reduced. | AND suggests practical methods of reducing costs
Q7 | One or more invoices received more than 60 days after invoice cut-off date. | On multiple occasions, invoices were received more than 30 days after invoice cut-off date. | Not more than one invoices received more than 30 days after the invoice cut-off date | All invoices for the rating period were received within 30 days of invoice cut-off date. | All invoices for the rating period were received within 30 days of invoice cut-off date.
| OR multiple invoices required MAJOR corrections. [MAJOR = incorrect hours, unapproved rates, improper expenses] | OR multiple invoices required minor corrections in billing. OR on one occasion had MAJOR corrections required. | On multiple invoices required minor corrections in billing. [Minor = simple mathematical errors having a value of less than $100 in value] | AND only minor corrections required on one invoice. | AND no corrections required
Q8 | Did not meet the project's established DBE/ESBE or SBE goals by more than 5% | Did not meet the project's established DBE/ESBE or SBE goals by more than 3% | Did not meet the project's established DBE/ESBE or SBE goals by more than 1% | Within 1% of the project's established DBE/ESBE or SBE goals | Exceeded the project's established DBE/ESBE or SBE goals by 3% or more.
| AND did not document a reasonable good-faith-effort. | AND did not document a reasonable good-faith-effort. | IF consultant documented a reasonable good-faith-effort, USE NA | USE NA if 0% target goal for project USE NA if Prime is DBE/ESBE/SBE
Q9 | Frequent instances of equipment not functioning OR not properly calibrated OR cited on one occasion of recording test results using equipment that was out of calibration. | Multiple instances of equipment not functioning, or not properly calibrated (with no instance of improperly recording test results using equipment that was out of calibration) OR at least one instance of not having equipment available OR fabrication delayed due to nonfunctioning equipment | Equipment was always available, but no more than one instance of equipment was not functioning AND materials testing did not delay fabrication | Equipment was always available, properly functioning, but had no more than one instance of equipment was not calibrated according to calibration schedule (when tested equipment was found to be within tolerance) | Equipment was always available. functioning, and calibrated according to schedule.
Quality
QUALITY
RATING
| 1 | 2 | 3 | 4 | 5
Q1 | At least one consultant removed from task at the direction of the State for failure to competently execute inspection duties. | On multiple occasions staff were cited for materials inspection or test deficiencies OR on one occasion was cited for a major deficiency in the performance of a materials inspection or test. [Major Deficiency = a deficiency that would lead to acceptance of substandard material] | Staff were cited for one incidence of a minor deficiency in the performance of a materials inspection or test. | Staff demonstrate the ability to perform materials inspection and testing without observable error. | Staff demonstrated an outstanding technical knowledge of materials inspection. [preinspection/ production/ curing and post production handling]
AND staff demonstrate the ability to perform materials testing without error.
Q2 | At least one consultant removed from task at the direction of the State for failure to competently execute inspection duties for lack of understanding contract requirements. | Staff were cited for not having at having a complete set of contract documents (standard specifications, special provisions, addenda, and approved working drawings). | Staff were cited for not having at having a complete set of contract documents (standard specifications, special provisions, addenda, and approved working drawings). | Staff were cited for not having at having a complete set of contract documents (standard specifications, special provisions, addenda, and approved working drawings). | Staff are always equipped with the correct contract documents (standard specifications, special provisions, addenda, and approved working drawings.).
|  | OR staff were cited for multiple incidences of applying incorrect compliance standards. | OR staff were cited for one incidence of applying incorrect compliance standards. | BUT staff were not cited for any incidences of applying incorrect compliance standards. | AND staff were not cited for any incidences of applying incorrect compliance standards.
Q3 | One consultant removed from task at the direction of the State for failure to competently execute inspection duties or follow NJDOTmaterials procedures. | Staff was cited on multiple occasions for failure to properly follow NJDOTmaterials procedures. | Staff was cited very few occasions for failure to properly follow NJDOTmaterials procedures | Staff was cited very few occasions for failure to properly follow NJDOTmaterials procedures with no instance of being cited for the same deficiency more than once. | Staff always competently executed inspection duties and NJDOTmaterials procedures.
Q4 | Reports were frequently incomplete, or insufficiently detailed. | Reports did not always contain basic details and resulted in gaps in inspection documentation. | Reports contain basic details, and sufficiently document inspections performed. | Reports contain basic details, and sufficiently document inspections performed. | Reports are consistently very detailed, and thoroughly document inspections performed.
| OR staff was cited for one Major error [incorrect data or calculations] OR for consistently having minor errors or omissions.. | OR staff were cited for multiple reports having minor errors [errors that do not misrepresent test results - e.g. project name, DP No.] | AND staff were cited for very few incidences of incomplete reports OR having very few minor errors or omissions. | AND reports are always complete and have no errors or omissions. | AND reports are always complete and have no errors or omissions.
Q5 | Reports are frequently submitted behind schedule by all staff. | On multiple occasions reports were submitted behind schedule and required direction by NJDOT to submit report | On multiple occasions reports were submitted behind schedule | Reports are usually completed and submitted on time, with very few occasions of reports submitted behind schedule. | Reports are consistently completed and submitted on time.
| OR on multiple occasions, reports had to be requested by NJDOT after 15 business days behind schedule. | OR on multiple occasions, reports were submitted more than 10 business days behind schedule. | OR on multiple occasions, reports were submitted more than 5 business days behind schedule.
Q6 | Staff communication skills are poor. On multiple occasions, failure to communicate or miscommunication resulted in worsening problems situations. | Staff communication is lacking. On at least one time, they failed to assertively communicate compliance requirements. | Staff usually communicate effectively. They assertively enforce compliance requirements. | Staff usually communicate effectively. They assertively enforce compliance requirements. | Staff communicate very effectively. They proactively communicate problems to NJDOT. Staff demonstrate an assertive enforcement of compliance requirements, and do so in am professional manner.
OR on at least one time failed to communicate a significant problem to NJDOT
| OR staff communication contributed to an unnecessarily hostile relationship. |  | Written and verbal communication did not result in any major problem. | Written and verbal communication is understood, and did not require undue clarification. | Written and verbal communication is clear and direct.
Q7 | Supervisory staff removed from task for failure to adequately provide oversight | Supervisory staff provide poor oversight or organization to inspection team. The Consultant is cited on multiple occasions for not observing essential activities | Supervisory staff provides adequate oversight or organization to inspection team. The Consultant is not cited for more than once incident of failing to monitor essential activities. | Supervisory staff monitor work and ensures all essential activities are monitored. Staff is not cited for failing to observe | Supervisory staff provide a high degree of oversight. Inspection team is very organized and all essential activities are monitored.
[Ability to monitor activities must be based on a reasonable work load and the number of staff]
Note on A38: firm may not score higher than a 4 if receiving a 4 or 5 for Quality #1 or 2, Unless most incidents of poor quality are identified by the firm and corrective measures taken.
Note on A62: Answer only on Final Rating